## TASK
No | TASK | 시작 | 종료 | 기간 | 대분류
1 | 기존 CPU Logic 분석 (3 Stage) | 2026-02-26 | 2026-02-28 | 3 | CPU 설계
2 | 5 Stage 필요 조건 분석 | 2026-03-01 | 2026-03-07 | 7 | CPU 설계
3 | Hazard 관련 Logic Study | 2026-03-08 | 2026-03-14 | 7 | CPU 설계
4 | SRAM Study(I/O, 동기/비동기, I-/D-) | 2026-03-15 | 2026-03-21 | 7 | CPU 설계
5 | CPU Logic 설계 | 2026-03-22 | 2026-04-04 | 14 | CPU 설계
6 | Logic 검증 (TB : #readmemh + $display) | 2026-04-05 | 2026-04-11 | 7 | CPU 설계
Formulas:
종료 = IF([기간]="","",[시작]+[기간]-1)
시작 = IF(OR(([기간, row above]=""),([TASK]="")),"",[종료, row above]+1)

## 오류사항분석
No | 오류사항 | 해결방법
1 | beq 타이밍 문제
2 | lw 타이밍 문제 | rd 레지스터를 버퍼를 둬서 한 사이클 더 가지고 있어야함 ++ mux로 memtoreg_flag 신호 가지고 rd 판단 ++ 대신 Registers에 들어가는 wdata도 memtoreg_flag로 판단
3 | 5-Stage RegWrite 타이밍 문제 | rd 레지스터 및 reg_wdata를 가지고 있어야함 최소 2,3개 버퍼를 둬야할듯
4 | regdst_mux | 생각해보니 ex 단계에서 만들어서 bridge로 output만 넘겨주면 되는 걸 굳이 wb mux, mem mux 만들었음 추후에 전면 수정 할것

## MemoryMap
Device | ADDR RANGE |  | BUS
BOOT ROM | 0x0000_0000 | 0x0000_03FF | AXI
TIMER | 0x00D0_A000 | 0x00D0_AFFF | APB
UART | 0x00D0_B000 | 0x00D0_BFFF | APB
I2C | 0x00D0_C000 | 0x00D0_CFFF | AHB
SPI | 0x00D0_D000 | 0x00D0_DFFF | AHB
GPIO | 0x00D0_E000 | 0x00D_0EFFF | APB
Interrupt Controller | TBD | TBD | AXI
DMA | 0x1000_0000 | 0x1000_FFFF | AXI
CACHE MEMORY | 0x2000_0000 | 0x2FFFF_FFFF | AXI
MAIN MEMORY | 0x3000_0000 | 0x7FFF_FFFF | AXI
AUX MEMORY | 0x8000_000 | 0xFFFF_FFF | APB

## 교안참고
MIPS Pipeline
Stage |  | Description
1 | IF | Instruction Fetch from Memory
2 | ID | Instruction Decode and Register Read
3 | EX | Execute Operation or Calculate ADDR
4 | MEM | Access Memory Operand
5 | WB | Write Result Back to Register

## 미구현명령어 정리
No | 명령어 | 정의(동작) | 구분방법 | 구현 유무
|  |  |  | verilogHDL | C
1 | bltz | Branch on Less Than Zero (< 0) | opcode = 6'b000001 (REGIMM), rt = 5'b0000 | X | O
2 | bgez | Branch on Greater Than or Equal to Zero (>= 0) | opcode = 6'b000001 (REGIMM), rt = 5'b0001 | X | O
3 | bltzal | Branch on Less Than Zero (< 0) And Link ($ra <= PC) | opcode = 6'b000001 (REGIMM), rt = 5'b1000 | X | O
4 | bgezal | Branch on Greater Than or Equal to Zero (>= 0) And Link ($ra <= PC) | opcode = 6'b000001 (REGIMM), rt = 5'b1001 | X | O
5 | jalr | Jump and Link Register | opcode = 6'b000000, funct_code = 6'b0001001 | X | O
6 | lbu | Load Byte Unsigned (opcode-rs-rt-imm <=> lbu rt, imm(rs)) (zero-extend) | opcode = 6'b100100 | X | O
7 | lb | Load Byte (opcode-rs-rt-imm <=> lb rt, imm(rs)) (sign-extend) | opcode = 6'b100000 | X | O
8 | lhu | Load Half-Word Unsigned (opcode-rs-rt-imm <=> lhu rt, imm(rs)) (zero-extend) | opcode = 6'b100101 | X | O
9 | lh | Load Half-Word (opcode-rs-rt-imm <=> lh rt, imm(rs)) (sign-extend) | opcode = 6'b100001 | X | O
10 | sb | Store Byte (opcode-rs-rt-imm <=> sb rt, imm(rs)) | opcode = 6'b100000 | X | O
11 | sh | Stroe Half-Word (opcode-rs-rt-imm <=> sh rt, imm(rs)) | opcode = 6'b100001 | X | O